## Full_Task_Estimates_with_Missin
Story | Task | Planning Suggestions | Estimated Days (Beginner Dev) | Hours (6h/day assumption) | Hours (8h/day assumption)
Infrastructure Setup | Refinement Terraform setup for AKS | Refine the pipeline to support AKS and test | 7 | 42 | 56
AKS Cluster Setup | Environment - DEV, UAT, PROD | Create separate clusters or namespaces per environment. Use Azure CLI or ARM templates. | 5 | 30 | 40
AKS Cluster Setup | Validate cluster health and access | Use kubectl get nodes, kubectl get pods, and Azure Monitor. Automate health checks via CI/CD pipelines. | 4 | 24 | 32
Frontend Packaging | Build frontend using CI/CD pipeline | Use GitLab or Azure DevOps. Inject environment variables securely. | 5 | 30 | 40
Frontend Packaging | Bundle and version artifacts | Maintain semantic versioning. Store artifacts in Nexus. | 3 | 18 | 24
Frontend Packaging | Run pre-deployment validations | Include linting, unit tests, and accessibility checks. Automate via pipeline stages. | 3 | 18 | 24
Frontend Deployment | Deploy using Helm charts or ARM templates | Use Helm for AKS. Validate values.yaml and secrets. ARM templates for infra provisioning. | 6 | 36 | 48
Frontend Deployment | Restructure Frontend for NEMO integration | Devpod deployment and restructuring | 5 | 30 | 40
Frontend Deployment | Validate deployment in AKS | Use kubectl describe, ingress validation, and smoke tests. | 4 | 24 | 32
Frontend Deployment | Integrate with Grafana/monitoring tools | Use Prometheus + Grafana stack. Define dashboards for key metrics. | 6 | 36 | 48
Backend Packaging | Containerize backend services with Docker | Use multi-stage builds. Scan images for vulnerabilities. | 5 | 30 | 40
Backend Packaging | Integrate secrets and environment configs | Use Azure Key Vault or sealed secrets. Avoid hardcoding. | 4 | 24 | 32
Backend Packaging | Run unit and integration tests | Automate via CI/CD. Use mocks for external dependencies. | 4 | 24 | 32
Backend Deployment | Deploy to AKS using manifests or Helm | Use Helm charts with RBAC and autoscaling configs. | 6 | 36 | 48
Backend Deployment | Configure service mesh and ingress | Use Istio or Linkerd. Define ingress rules and TLS certs. | 6 | 36 | 48
Backend Deployment | Validate endpoints and service health | Use readiness/liveness probes. Monitor via Azure Monitor. | 5 | 30 | 40
Backend Deployment | (Flask API) for Deployment | Containerize the flask, kubernetes deployment & service YAML for backend | 5 | 30 | 40
AKS Deployment | push docker image to ACR, apply kubernetes manifest | Push docker image to ACR, apply kubernetes manifest | 5 | 30 | 40
Monitoring & Rollback | Setup Grafana/Prometheus dashboards | Define SLIs/SLOs. Use templated dashboards for reuse. | 6 | 36 | 48
Monitoring & Rollback | Define rollback strategy and scripts | Use Helm rollback, GitOps versioning, and backup plans. | 4 | 24 | 32
Monitoring & Rollback | Conduct smoke tests post-deployment | Automate via Postman or Cypress. Include API and UI checks. | 3 | 18 | 24
Infrastructure Setup | Refinement Terraform setup for AKS | Refine the pipeline to support AKS and test | 7 | 42 | 56
CI/CD Setup | Design & implement CI/CD pipelines (build-test-deploy) | Use GitLab/Azure DevOps pipelines with YAML templates | 7 | 42 | 56
CI/CD Setup | Add automated quality checks & triggers in pipeline | Add linting, unit tests, code coverage, PR triggers | 5 | 30 | 40
Security & Compliance | Implement RBAC & network policies in AKS | Define fine-grained RBAC roles; apply network policies per namespace | 6 | 36 | 48
Security & Compliance | Integrate vulnerability scanning & secret rotation | Use Trivy/Aqua for scanning, Key Vault for secrets | 6 | 36 | 48
Database & Services | Provision database (e.g., PostgreSQL) & integrate with app | Use managed DB from Azure, configure secrets for connection | 7 | 42 | 56
Logging & Observability | Setup centralized logging (ELK/Azure Monitor) | Ship logs to ELK/Log Analytics; create standard dashboards | 6 | 36 | 48
Logging & Observability | Implement distributed tracing (OpenTelemetry/Jaeger) | Add tracing middleware; visualize traces in Jaeger/Grafana Tempo | 6 | 36 | 48
Scalability & Resilience | Configure autoscaling (HPA/VPA) | Define HPA rules; validate under load tests | 5 | 30 | 40
Scalability & Resilience | Run resilience/chaos tests | Inject failures (Chaos Mesh, Azure Chaos Studio) | 6 | 36 | 48
Documentation & Handover | Write developer onboarding guide | Document local setup, pipeline usage, and deployment steps | 3 | 18 | 24
Documentation & Handover | Write ops monitoring & rollback guide | Document monitoring dashboards, alerts, rollback playbook | 3 | 18 | 24